## Sheet1
Project Dashboard
| Primary Project Information |  | Further Project Information |  |  | Project Metrics
| Project Name: | Implementation of ERP | Start Date: |  | 01-Dec-2012 |  | Projected | Actual
| Project Code: | 99879 | End Date: |  | 31-Mar-2013 | Cost | 3987786 | 3443231
| Project Manager: | Nooruddin Surani | Location: |  | Karachi, Pakistan | Revenue | 398778.6 | 309890.79
| Last Forecast Date: | 30-Nov-2012 | Project Status: |  | In Progress | Earned Value |  | 3561083
| Project Activity by Task (Top 5 by Cost) |  |  | Pending Tasks by Priority |  | Project Metrics
Time Remaining
120
Hours Remaining
|  |  |  | Tasks by Release |  | Cost Metrics
Cost Remaining
544,555
USD Remaining
|  |  |  | Current Velocity |  | Required Velocity
|  |  |  | 3.20 hrs/day |  | 3.95 hrs/day

## Sheet2
Property Purchase | 3500000
Civil Material & Supply | 450650
Management Fee | 201234
Across Road Construction | 200688
Admin Expenses | 55000
Low | 23
Medium | 55
High | 44
Phase I | 54
Phase II | 32
Phase III | 76