## Sheet1
PORTFOLIO DASHBOARD
Projects Health | [5 empty] | Portfolio Summary |  |  | Portfolio Status |  | Project by Red Lights
Projects | Project A | Project B | Project C | Project D | Project E | Number of Projects
Time | 28 | 49 | 30 | 37 | 60 | Cost
Cost | 17 | 62 | 88 | 89 | 42 | Planned Cost |  | 970666
Resource | 64 | 54 | 14 | 23 | 32 | Estimated Cost |  | 952771
Progress | 35 | 70 | 18 | 44 | 43 | Actual Cost |  | 965063
Effieciency | 51 | 39 | 24 | 14 | 15 | Percentage of Budget |  | 72%
Overalll | 39 | 54.8 | 34.8 | 41.4 | 38.4 | Average Values
[6 empty] | Percent Complete |  | 51%
[6 empty] | Planned Project Duration |  | 138 D
[6 empty] | Actual Project Duration |  | 118 D
[6 empty] | Planned Cost |  | 194133.2
[6 empty] | Estimated Cost |  | 190554.2
[6 empty] | Actual Cost |  | 193012.6
Projects by Percent Complete |  |  |  | Projects by Planned Cost |  |  | Cost |  |  | Risk
Planned Resource Work | [7 empty] | Planned Portfolio Cost

## Sheet2
Projects | Project A | Project B | Project C | Project D | Project E
Time | 28 | 49 | 30 | 37 | 60
Cost | 17 | 62 | 88 | 89 | 42
Resource | 64 | 54 | 14 | 23 | 32
Progress | 35 | 70 | 18 | 44 | 43
Effieciency | 51 | 39 | 24 | 14 | 15
Overalll | 39 | 54.8 | 34.8 | 41.4 | 38.4
1
| A | B | C | D | E
Time | 28 | 49 | 30 | 37 | 60
Number of Projects
No Red light |  | 1
1 Red Light |  | 1
3 Red Light |  | 2
4 Red Light |  | 3
5 Red Light |  | 3
by Percent Complete
0 - 25 % | 4
26 - 50 % | 3
51 -75 % | 2
76 - 100 % | 3
By Planning Cost
Less than 100000 | 2
from 100000 - 500000 | 3
greater than 500000 | 5
| Actual | Planned | Baseline
A | 21515 | 47903 | 34192
B | 16760 | 46698 | 30829
C | 21134 | 41892 | 10851
D | 45170 | 27108 | 40367
E | 20153 | 38015 | 18130
Risk | probability | Impact | Exposure
Risk A | 38 | 5 | 190
Risk B | 71 | 5 | 94
Risk C | 61 | 3 | 10
Risk D | 11 | 9 | 9
Risk 4 | 70 | 6 | 10
Year | month | hours |  | Year | month | Cost
2012 | Jan | 1354 |  | 2012 | Jan | 14597
| Feb | 1862 |  |  | Feb | 43898
| Mar | 1010 |  |  | Mar | 33214
| Apr | 1151 |  |  | Apr | 14923
| May | 1200 |  |  | May | 47835
| Jun | 1290 |  |  | Jun | 14027
| Jul | 1373 |  |  | Jul | 11306
| Aug | 1697 |  |  | Aug | 15040
| Sep | 991 |  |  | Sep | 21026
| Oct | 1725 |  |  | Oct | 31089
| Nov | 1693 |  |  | Nov | 34052
| Dec | 1542 |  |  | Dec | 12740
2013 | Jan | 1003 |  | 2013 | Jan | 17724
| Feb | 1280 |  |  | Feb | 34167
| Mar | 1683 |  |  | Mar | 49951
Planned Cost |  |  | 970666
Estimated Cost |  |  | 952771
Actual Cost |  |  | 965063
Percentage of Budget |  |  | 72
Average Values
Percent Complete |  |  | 51
Planned Project Duration |  |  | 138
Actual Project Duration |  |  | 118
Planned Cost |  |  | 194133.2
Estimated Cost |  |  | 190554.2
Actual Cost |  |  | 193012.6
|  | last yr | current yr | projection
Value | Max | 60000 | 51825 | 100000
51.825 | 100 | 60 | 51.825
Graph
0 | 0
0.057303 | 0.99836
0 | 0
Doughnut
100 | 0
60
40